## Blad1
Task | Description | Start date | Days for the task | Deadlines
1 | plan of approach | 2017-03-20 | 7 | 1
1A | Project description | 2017-03-20 | 2
1B | Requirements and wishes | 2017-03-22 | 2
1C | Planning | 2017-03-24 | 3
2 | Simulation swarm + loader | 2017-03-21 | 31 | 1
2A | Simulation swarm | 2017-03-21 | 14
2B | Simulation loader | 2017-03-31 | 14
2C | Simulation swarm + loader | 2017-04-10 | 11
3 | Robot loader design | 2017-03-21 | 31 | 1
3A | Robot design concepts | 2017-03-21 | 3
3B | Prototyping | 2017-03-24 | 7
3C | Rough design | 2017-03-31 | 7
3D | Testing | 2017-04-07 | 7
3E | Final design | 2017-04-14 | 7
4 | Risk identification | 2017-03-31 | 3
5 | Risk reduction methodology | 2017-04-07 | 14
6 | Swarm with robot to robot transfer | 2017-04-20 | 50 | 1
6A | Swarm with leds | 2017-04-20 | 20
6B | Robot to robot transfer | 2017-04-30 | 20
6C | Swarm with robot to robot transfer | 2017-05-10 | 30
7 | Robot control system | 2017-06-12 | 7 | 1
8 | Description of robot logic | 2017-06-12 | 7 | 1
9 | Buffer time | 2017-06-19 | 12
10 | Buffer time | 2017-06-30 |  | 1